## Legend and Setup
KenAddme IT Links - Project Build Status Tracker
Two aligned governance tracks: Project Management (Gates 1-7) and Software Development & Engineering (G0-G6)
How to use this workbook
- Fill in only the shaded cells. Every unshaded cell is either a heading, a framework requirement or a formula.
- Project details below feed nothing automatically - they are the controlled header for the whole tracker. Complete them first.
- 'PM Track' and 'SDLC Track' hold one row per mandatory evidence item. Set the Status column from the drop-down list, name an owner, and record where the evidence actually lives.
- 'Dashboard' calculates gate completion from those two sheets. Do not type over its formulas.
- Set a row to 'Not applicable' only where tailoring permits it. Tailoring must not fall below the Appendix A artefact floor without an approved exception - log that exception on the 'Exceptions' sheet.
- A gate is not passed because the work is finished. It is passed when the evidence exists, the named authority decides, and the decision is recorded.
Example of a completed tracker row
Column | Example entry | Note
Gate | G2 | Pre-filled - do not edit
Required evidence | Threat model and privacy assessment | Pre-filled - do not edit
Status | Complete | Choose from the drop-down list
Owner | A. Mensah, Security and Privacy Reviewer | One named person, not a team
Due date | 2026-10-24 | Use YYYY-MM-DD
Date completed | 2026-10-21 | Blank until the evidence is accepted
Evidence reference | REPO/docs/security/threat-model-v2.md (rev 2026-10-21) | Where the record actually lives
Notes | Two residual risks accepted by the Sponsor at G2 | Conditions, deviations, links
Project details
Field | Value | Guidance
Project / product name |  | Name as it appears in the project register
Project register ID |  | Unique reference
Project class (PM) |  | Class A - Strategic/High Risk ¦ Class B - Standard/Medium Risk ¦ Class C - Small/Low Risk
Software class (SDLC) |  | Class 1 Experimental ¦ Class 2 Standard ¦ Class 3 High ¦ Class 4 Critical
Classification rationale |  | Highest applicable condition controls the class
Executive / Project Authority |  | Chair or recorded delegate
Project Sponsor |  | Accountable business owner
Project Manager / Delivery Lead |  | Cannot approve own charter, baseline, change, release, acceptance or closure
Product / Business Owner
Technical Lead / Solution Architect
Quality / Assurance Reviewer |  | Independence depth follows the higher class
Security / Privacy Reviewer |  | Distinct control role for higher-risk work
Service / Operations Owner |  | Owns operational acceptance and benefits evidence
Release Authority |  | Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2
Data Owner
Cost baseline (GHS) |  | Approved baseline excluding contingency
Cost tolerance |  | Class A +/-5%, Class B +/-10%, Class C +/-15%
Schedule tolerance |  | Class A +/-5%, Class B +/-10%, Class C +/-15%
Baseline start date
Baseline completion date
Default Gate 7 due date |  | Class A 6 months after Gate 6; Class B 6 months; Class C 90 days
Personal data in scope? |  | If yes, assess Data Protection Act 2012 (Act 843)
Cybersecurity service in scope? |  | If yes, assess Cybersecurity Act 2020 (Act 1038)
Publicly funded? |  | If yes, assess Public Procurement Act 2003 (Act 663) as amended by Act 914
Tailoring decisions recorded |  | Tailoring must not fall below the Appendix A floor
Role separation position |  | Section 3.3 met, or compensating assurance approved by the Project Authority
Source documents
- KenAddme IT Links Project Management Framework v1.1 (Approved 2 September 2026, effective 31 October 2026)
- KenAddme IT Links Software Development and Engineering Framework v1.2 (Approved 2 September 2026, effective 31 October 2026)
Framework owner and custodian: Freston Kenny Adedeme (Framework Owner and Custodian)

## Dashboard
Build status dashboard
Counts are calculated from the two track sheets. Record the gate decision and date here once the named authority has decided.
Track | Gate | Decision point | Items | Complete | In progress | Not applicable | Outstanding | % complete | Evidence position | Gate decision | Decision date
PM | Gate 1 | Intake decision | 11 | 0 | 0 | 0 | 11 | 0% | 11 item(s) outstanding | Not yet held
PM | Gate 2 | Project authorisation | 12 | 0 | 0 | 0 | 12 | 0% | 12 item(s) outstanding | Not yet held
PM | Gate 3 | Delivery readiness | 16 | 0 | 0 | 0 | 16 | 0% | 16 item(s) outstanding | Not yet held
PM | Gate 4 | Major deliverable or release readiness | 12 | 0 | 0 | 0 | 12 | 0% | 12 item(s) outstanding | Not yet held
PM | Gate 5 | Continuation or exception decision | 10 | 0 | 0 | 0 | 10 | 0% | 10 item(s) outstanding | Not yet held
PM | Gate 6 | Closure approval | 12 | 0 | 0 | 0 | 12 | 0% | 12 item(s) outstanding | Not yet held
PM | Gate 7 | Benefits confirmation | 10 | 0 | 0 | 0 | 10 | 0% | 10 item(s) outstanding | Not yet held
PM | All | Track total | 83 | 0 | 0 | 0 | 83 | 0% | 83 item(s) outstanding across the track
SDLC | G0 | Intake | 8 | 0 | 0 | 0 | 8 | 0% | 8 item(s) outstanding | Not yet held
SDLC | G1 | Requirements baseline | 12 | 0 | 0 | 0 | 12 | 0% | 12 item(s) outstanding | Not yet held
SDLC | G2 | Design readiness | 11 | 0 | 0 | 0 | 11 | 0% | 11 item(s) outstanding | Not yet held
SDLC | G3 | Code complete | 13 | 0 | 0 | 0 | 13 | 0% | 13 item(s) outstanding | Not yet held
SDLC | G4-R | Release recommendation (verification and acceptance) | 11 | 0 | 0 | 0 | 11 | 0% | 11 item(s) outstanding | Not yet held
SDLC | G4 | Release readiness authorisation | 11 | 0 | 0 | 0 | 11 | 0% | 11 item(s) outstanding | Not yet held
SDLC | G5 | Operational acceptance | 13 | 0 | 0 | 0 | 13 | 0% | 13 item(s) outstanding | Not yet held
SDLC | G6 | Retirement / closure | 10 | 0 | 0 | 0 | 10 | 0% | 10 item(s) outstanding | Not yet held
SDLC | All | Track total | 89 | 0 | 0 | 0 | 89 | 0% | 89 item(s) outstanding across the track
Reminder: a gate may be approved with conditions only when the conditions have owners and deadlines. Unresolved critical conditions cannot be treated this way, and a critical non-conformance blocks the gate unless a lawful, safe and time-bound exception is authorised.

## PM Gates 1-7
Project Management Track
Source: Project Management Framework v1.1. One row per mandatory evidence item. Set Status, Owner and Evidence reference.
Gate | Gate decision point | Stage | Item | Required evidence | Decision owner / approver | Status | Owner | Due date | Date completed | Evidence reference | Notes
Gate 1 - Intake decision
Exit criteria: The need is real enough to investigate, an idea owner is identified, the work supports institutional or client value, and feasibility effort is justified.
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.01 | Project idea / intake record: problem or opportunity, proposed outcome, beneficiaries, owner, urgency and known constraints | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.02 | Current situation described with evidence that a problem or opportunity exists | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.03 | Affected users, clients, services and institutional goals identified | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.04 | Expected outcome stated without assuming a solution too early | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.05 | Initial screening for legal, ethical, security, privacy, safety, financial and reputational concerns | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.06 | Urgency, rough scale and project-versus-operations judgement recorded | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.07 | Comparison against active commitments and resource capacity | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.08 | Initial classification proposed (Class A / B / C) with reasons | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.09 | Portfolio recommendation: proceed to feasibility, defer, merge, return or decline | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.10 | Gate 1 decision recorded with approver, date and conditions | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 1 | Intake decision | Stage 1 - Strategic Intake and Opportunity Definition | Gate 1.11 | Expedited Gate 1/2 path used? If yes, record urgency justification, authority, maximum spend, time limit and stop authority (Section 4.6) | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B | Not started
Gate 2 - Project authorisation
Exit criteria: A sponsor accepts accountability; the business case is credible; scope and intended outcome are clear; major risks are understood; suitable resources are likely available; and feasibility evidence supports proceeding.
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.01 | Project charter completed against the Appendix B template | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.02 | Proportionate business case prepared | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.03 | Feasibility assessed: strategic, technical, operational, economic, schedule, legal/contractual, ethical/social and resource dimensions | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.04 | Alternative approaches identified, including do nothing, buy, build, partner or change the process | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.05 | High-level scope, exclusions, assumptions and acceptance concept prepared | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.06 | Cost, duration, resource demand and expected benefits estimated as ranges where uncertainty is high | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.07 | Principal risks, dependencies and constraints identified | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.08 | Sponsor, project manager and key decision makers nominated | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.09 | Software framework alignment recorded in the charter (software class, aligned G0-G6 checkpoints, Appendix I mapping) | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.10 | Governance and tolerances recorded: decision rights, reporting, escalation, role separation, financial band, change authority | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.11 | Benefits ownership, measures, default Gate 7 date and protected review effort recorded | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 2 | Project authorisation | Stage 2 - Initiation and Feasibility | Gate 2.12 | Gate 2 decision recorded with approver, date and conditions | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 - Delivery readiness
Exit criteria: The integrated plan is realistic; funds and people are committed; key requirements and acceptance criteria are testable; material risks have responses; controls and reporting are ready; and the sponsor formally authorises execution.
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.01 | Scope statement, deliverables, exclusions, requirements and acceptance criteria | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.02 | Work breakdown structure with manageable work packages | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.03 | Schedule with dependencies, milestones, estimates, critical constraints and contingency | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.04 | Budget, procurement, staff effort, tools, infrastructure and reserves | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.05 | Responsibility assignment and decision authority (Appendix H, one accountable per activity) | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.06 | Quality plan, review points, test strategy and evidence required for acceptance | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.07 | Risk register, response actions, issue process and escalation thresholds | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.08 | Communication, stakeholder engagement and reporting calendar | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.09 | Security, privacy, data, access, backup, continuity and release controls where relevant | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.10 | Change, configuration, version, document and records management method | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.11 | Transition, training, support, handover, rollback and closure approach | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.12 | Funded benefits-review effort, operational benefit owner and default Gate 7 due date | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.13 | Baseline quality tests passed: complete, consistent, achievable, controlled, acceptable | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.14 | Role separation meets Section 3.3, or compensating assurance approved and recorded | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.15 | Plan readiness checklist (Appendix C) signed by Sponsor, PM and reviewers | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 3 | Delivery readiness | Stage 3 - Detailed Planning and Baseline Approval | Gate 3.16 | Gate 3 decision recorded with approver, date and conditions | Sponsor for Class B/C; Project Authority for Class A | Not started
Gate 4 - Major deliverable or release readiness
Exit criteria: The deliverable meets agreed requirements; tests and reviews are evidenced; unresolved defects and risks are within approved limits; operations and users are ready; security and privacy conditions are satisfied; and release or transition authority is granted.
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.01 | Formal kickoff held confirming objectives, roles, ways of working, reporting and escalation | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.02 | Work packages authorised with outputs, owners, dates, quality criteria and dependencies | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.03 | One controlled source maintained for plans, decisions, risks, issues, changes and deliverable versions | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.04 | Deliverables reviewed early and progressively rather than at final testing only | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.05 | Vendors, external contributors and client dependencies controlled against agreed obligations | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.06 | Users, operations, training, support, data migration and release environments prepared in parallel | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.07 | Work package acceptance evidence: output exists, checks passed, defects resolved or formally accepted, documentation updated, reviewer accepted | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.08 | Test and review evidence identifying deliverable version and test environment | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.09 | Defect and risk position within approved limits | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.10 | Operational and user readiness confirmed | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.11 | Security and privacy conditions satisfied | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 4 | Major deliverable or release readiness | Stage 4 - Execution and Team Coordination | Gate 4.12 | Gate 4 decision recorded with acceptance authority, date and conditions | Named acceptance authority; Project Authority concurrence for Class A | Not started
Gate 5 - Continuation or exception decision
Exit criteria: Forecast performance remains acceptable, or a credible recovery/rebaseline decision has been approved. If value has disappeared, risk is unacceptable or recovery is not credible, the project must be paused, redirected or terminated.
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.01 | Status reporting running at the class cadence (Class A weekly review plus formal status fortnightly; Class B monthly with fortnightly team review; Class C monthly plus midpoint check beyond 20 business days) | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.02 | Minimum status report content complete: overall status, achievements, next period, schedule, cost/resources, scope/quality, risks/issues, decisions required | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.03 | Status colour supported by evidence, not by activity or an unexpired deadline | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.04 | Tolerance position measured against approved cost, schedule, scope, quality and risk limits | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.05 | Variance analysis with root causes, consequences and corrective options | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.06 | Gate 5 trigger log maintained (escalation trigger, forecast tolerance breach, material change, rebaseline, funding release, supplier failure, recovery plan, critical dependency change, doubtful acceptance, or a call by Sponsor/Authority/assurance) | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.07 | Gate 5 convened within 2 business days for a red condition and 5 business days for any other material trigger | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.08 | Corrective actions implemented, affected plans updated and effectiveness verified | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.09 | Rebaseline decisions retain original commitment, approved changes and current forecast | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 5 | Continuation or exception decision | Stage 5 - Continuous Monitoring, Control and Corrective Action (recurring from Gate 3 to Gate 6) | Gate 5.10 | Gate 5 decision recorded with approver, date and conditions | Sponsor within tolerance; Project Authority beyond tolerance or for Class A | Not started
Gate 6 - Closure approval
Exit criteria: The authorised client or sponsor has accepted the outcome; operations own it; outstanding actions are assigned; finances and contracts are reconciled; records are archived; and the sponsor approves project closure.
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.01 | Formal acceptance obtained against approved criteria, with accepted limitations recorded | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.02 | Release, migration, training, support, security, backup, recovery and operational-readiness actions complete | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.03 | Ownership transferred: products, data, licences, environments, documentation and unresolved actions | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.04 | Contracts, invoices, assets, accounts and access rights closed or handed over | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.05 | Budget reconciled; final cost, schedule, scope and quality performance recorded | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.06 | Current versions, approvals, evidence, decisions, lessons and closure records archived | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.07 | People and resources released responsibly and contributions acknowledged | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.08 | Benefits measures, owners, review dates and outstanding corrective actions assigned | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.09 | Records reviewed against the Appendix J retention schedule; legal holds identified | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.10 | Project register status set to 'Operational - Benefits Pending' with Gate 7 due date and evidence owner | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.11 | Closure report completed (Appendix G) | Project Sponsor | Not started
Gate 6 | Closure approval | Stage 6 - Transition, Acceptance and Closure | Gate 6.12 | Gate 6 decision recorded with approver, date and conditions | Project Sponsor | Not started
Gate 7 - Benefits confirmation
Exit criteria: Benefits evidence is reviewed, remaining actions have owners, important lessons are incorporated into institutional practice and leadership decides whether to sustain, improve, expand, replace or retire the outcome.
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.01 | Benefits plan complete: benefit, baseline, measure, target, owner, dependencies and review dates | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.02 | Protected review effort used as budgeted at Gate 3 (Class A two person-days, Class B one, Class C half) | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.03 | Usage evidence gathered: is the product or capability being used as intended? | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.04 | Outcome evidence gathered: service, revenue, efficiency, learning, quality, safety or client improvement | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.05 | Costs, delays, negative impacts or risks transferred elsewhere identified | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.06 | Correct and incorrect assumptions reviewed | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.07 | Corrective actions, follow-on investment or retirement decisions identified with owners | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.08 | Lessons routed into institutional standards or training content | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.09 | Project register status changed to 'Closed - Benefits Reviewed' | Project Sponsor, supported by the Service / Operations Owner | Not started
Gate 7 | Benefits confirmation | Stage 7 - Benefits Realisation and Post-Project Review | Gate 7.10 | Gate 7 decision recorded with approver, date and conditions | Project Sponsor, supported by the Service / Operations Owner | Not started

## SDLC G0-G6
Software Development and Engineering Track
Source: Software Development and Engineering Framework v1.2. One row per mandatory evidence item. Set Status, Owner and Evidence reference.
Gate | Gate decision point | Stage | Item | Required evidence | Decision owner / approver | Status | Owner | Due date | Date completed | Evidence reference | Notes
G0 - Intake
Exit criteria: The problem and intended benefits are clear enough to investigate; ownership and discovery resources are assigned; material legal, privacy, security or procurement blockers are identified; and management has approved, deferred or declined in writing.
G0 | Intake | Stage 1 - Initiation and feasibility | G0.01 | Project request or concept note | Sponsor and delivery lead | Not started
G0 | Intake | Stage 1 - Initiation and feasibility | G0.02 | Preliminary business case and feasibility assessment (technical, economic, operational, schedule, legal, data, security, resource) | Sponsor and delivery lead | Not started
G0 | Intake | Stage 1 - Initiation and feasibility | G0.03 | Named sponsor, delivery lead and technical owner | Sponsor and delivery lead | Not started
G0 | Intake | Stage 1 - Initiation and feasibility | G0.04 | Initial scope, stakeholder list, risk class and risk register | Sponsor and delivery lead | Not started
G0 | Intake | Stage 1 - Initiation and feasibility | G0.05 | Alternatives considered, including process change, configuration or acquisition instead of custom development | Sponsor and delivery lead | Not started
G0 | Intake | Stage 1 - Initiation and feasibility | G0.06 | Discovery effort estimated and authority to proceed obtained | Sponsor and delivery lead | Not started
G0 | Intake | Stage 1 - Initiation and feasibility | G0.07 | G0 decision record | Sponsor and delivery lead | Not started
G0 | Intake | Stage 1 - Initiation and feasibility | G0.08 | No coding started as an informal commitment before owner, outcome, data constraints and acceptance authority exist | Sponsor and delivery lead | Not started
G1 - Requirements baseline
Exit criteria: Each committed requirement is necessary, clear, feasible, testable, traceable and prioritised; conflicts and ambiguities are resolved or assigned with dates and owners; the acceptance authority approves the baseline; and scope, schedule and cost assumptions align with the approved requirements.
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.01 | Software Requirements Specification, product backlog or equivalent controlled requirements set | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.02 | Functional requirements, business rules, data needs, interfaces, roles and permissions documented | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.03 | Non-functional requirements defined: security, privacy, performance, availability, reliability, accessibility, usability, compatibility, maintainability, scalability, portability, logging, backup and recovery | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.04 | User journeys, process maps, use cases or stories as appropriate | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.05 | Acceptance criteria and initial test conditions | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.06 | Data inventory and classification (Public / Internal / Confidential / Restricted) | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.07 | Preliminary privacy and security requirements | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.08 | Requirements traceability matrix or linked work-item structure | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.09 | Requirements reviewed with affected stakeholders and formally baselined | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.10 | Requirement quality rules applied: clear, atomic, feasible, testable, traceable, consistent, controlled | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.11 | Unresolved-question log with owners and dates | Product owner and delivery lead | Not started
G1 | Requirements baseline | Stage 2 - Discovery and requirements engineering | G1.12 | G1 approval recorded | Product owner and delivery lead | Not started
G2 - Design readiness
Exit criteria: The design addresses the approved functional and non-functional requirements; interfaces, data ownership, trust boundaries and failure modes are understood; critical risks are reduced, accepted or assigned to a dated action; and build, test, deployment and operational approaches are feasible and funded.
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.01 | Project delivery plan and updated estimates | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.02 | Assurance effort, schedule and budget as a distinct line item; commercial disclosure for Class 3 and Class 4 client work | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.03 | Architecture description with context, component, deployment and data-flow views | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.04 | Architecture Decision Records for material choices, including rejected alternatives | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.05 | UX prototypes/designs, database model and API/interface specifications | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.06 | Threat model and privacy assessment | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.07 | Security design: authentication, authorisation, secrets, encryption, logging and recovery controls | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.08 | Test strategy, environment plan, migration approach, observability, support model, backup and rollback concept | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.09 | Risky assumptions validated with controlled prototypes or spikes | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.10 | Architecture expectations addressed: modularity, least privilege, failure containment, observability, recoverability, technology fitness | Technical lead; security reviewer for higher risk | Not started
G2 | Design readiness | Stage 3 - Planning, architecture and detailed design | G2.11 | G2 review and approval record | Technical lead; security reviewer for higher risk | Not started
G3 - Code complete
Exit criteria: All committed work is merged through the approved review path; the build is reproducible and automated checks pass or have approved exceptions; no unresolved critical defect, exposed secret or prohibited component is known; and the test environment holds an identifiable release candidate.
G3 | Code complete | Stage 4 - Implementation and integration | G3.01 | Version-controlled source code, configuration and infrastructure definitions | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.02 | Work items, commits and pull/merge requests linked with reviewer evidence | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.03 | Protected release branches enforced; merges require successful checks and review | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.04 | Peer review completed (two-person or specialist review for critical security, data, payment or infrastructure changes) | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.05 | Unit tests written with the code; integration, contract or component tests added where interfaces are affected | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.06 | Continuous integration passing: formatting, linting, build, test, secret and dependency/security scans | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.07 | Successful automated build and test results retained | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.08 | Dependency and licence inventory; software bill of materials where required | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.09 | Secrets held in an approved secret store and absent from code, fixtures, logs and collaboration tools | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.10 | AI- or tool-generated code reviewed, tested and accepted by a competent human | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.11 | Architecture, API, data, operational and user documentation updated with the change | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.12 | Known-defect, technical-debt and deviation records | Technical lead and QA lead | Not started
G3 | Code complete | Stage 4 - Implementation and integration | G3.13 | G3 code-complete decision | Technical lead and QA lead | Not started
G4-R - Release recommendation (verification and acceptance)
Exit criteria: Every release requirement has passed evidence or an explicitly accepted deviation; no open Severity 1 or unaccepted Severity 2 defect remains; security, privacy and operational risks meet the release criteria; and the release candidate and evidence set are uniquely identified and protected from uncontrolled change.
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.01 | Approved risk-based test plan with traceability to requirements | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.02 | Test cases, automated suites, actual results and evidence recorded with environment, build identifier and tester | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.03 | Unit, integration, contract, system, regression and user-acceptance tests executed as applicable | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.04 | Security, privacy, performance, accessibility, compatibility, migration, backup/restore and resilience testing according to risk | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.05 | Production-like environments used with representative, lawful test data and no uncontrolled production-data copying | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.06 | Defect register with severity, disposition, owner and retest status | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.07 | Corrections retested and targeted regression tests run | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.08 | No open S1 defect; any S2 released only with documented residual-risk acceptance | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.09 | Security/privacy scan and review records | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.10 | User-acceptance record from the authorised product owner or client representative | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4-R | Release recommendation (verification and acceptance) | Stage 5 - Verification, validation and acceptance | G4-R.11 | G4 recommendation issued | QA lead and product owner; independent QA for Class 3, independent or specialist QA for Class 4 | Not started
G4 - Release readiness authorisation
Exit criteria: Release approval is recorded before production change except under the emergency-change process; deployment completed successfully or rollback restored the approved service state; monitoring shows acceptable service health; and support and service owners accept the deployed version and known issues.
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.01 | Release package assembled: version, approved changes, dependencies, configuration, migration and known limitations | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.02 | Release notes and immutable release/build identifier | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.03 | Production access, infrastructure, capacity, monitoring, backup, support and communication readiness confirmed | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.04 | Approved deployment, data migration, rollback and communication plans with named decision authority | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.05 | Build and deployment credentials kept separate; deployment automated and repeatable where practical | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.06 | Affected data backed up or checkpointed; restoration or rollback feasibility validated before irreversible change | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.07 | Operational runbook, monitoring/alert configuration and support handover ready | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.08 | Release-readiness checklist (Appendix F) completed across scope, requirements, code, tests, security/privacy, dependencies, data, operations, deployment and approval | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.09 | Release authority is not the sole author of the release (role separation for Class 3-4) | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.10 | Deployment executed with smoke tests and business verification; actual deployment, deviations, approvers and outcome recorded | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G4 | Release readiness authorisation | Stage 6 - Release and deployment | G4.11 | G4 release authorisation recorded | Product owner, service owner and release authority (Executive Sponsor or delegate for Class 3-4; Technical Lead for Class 1-2) | Not started
G5 - Operational acceptance
Exit criteria: The service remains within approved operational and security limits; incidents, vulnerabilities and maintenance obligations have accountable owners and target dates; access, dependencies, data retention and continuity controls are reviewed periodically; and management receives sufficient evidence to continue, improve, replace or retire the service.
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.01 | Service catalogue entry, named service owner and support model | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.02 | Deployment record, smoke tests and early-life review | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.03 | Monitoring of availability, performance, capacity, errors, security events, backups, certificate expiry and critical dependencies | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.04 | Documented support channels, service hours, escalation paths and response targets | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.05 | Incident, problem, change, maintenance and vulnerability records | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.06 | Root-cause analysis for significant or recurring incidents with tracked corrective actions | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.07 | Vulnerability remediation within service targets (critical: 7 days Class 3-4, 14 days Class 2; high: 30 days Class 3-4, 60 days Class 2) | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.08 | S1 incident acknowledgement within target (1 hour Class 3-4, 4 hours Class 2) | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.09 | Backup restoration tested on schedule (quarterly Class 3-4, at least semi-annually Class 2) with results compared to RPO/RTO | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.10 | Access review completed on schedule (quarterly Class 3-4, at least annually Class 2) | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.11 | Enhancements and changes processed through the same traceability, review, testing and release controls | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.12 | Service review reports and improvement backlog maintained | Service owner and product owner | Not started
G5 | Operational acceptance | Stage 7 - Operations, maintenance and support | G5.13 | G5 operational acceptance recorded | Service owner and product owner | Not started
G6 - Retirement / closure
Exit criteria: Users and stakeholders have been notified and supported through transition; required data is preserved or transferred and unneeded data securely disposed of; no orphaned credential, public endpoint, paid service or unmanaged dependency remains; and the sponsor, data owner and service owner approve closure.
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.01 | Retirement reason, affected users, replacement service, dependencies and approved date confirmed | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.02 | Transition and communication plan, including data export or migration | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.03 | Retention, archival, transfer or secure-deletion decisions applied to data and records | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.04 | Accounts, credentials, integrations, domains, certificates, pipelines, infrastructure and supplier services disabled | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.05 | Source, releases, configuration, decisions, test evidence, licences and operational records archived | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.06 | Final asset inventory and archive location recorded | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.07 | Financial and contractual closure verified | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.08 | Lessons learned, benefits achieved and outstanding actions captured | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.09 | Client or sponsor acceptance recorded | Sponsor, data owner and service owner | Not started
G6 | Retirement / closure | Stage 8 - Retirement and project closure | G6.10 | G6 closure decision | Sponsor, data owner and service owner | Not started

## Artefact Floor
Appendix A - mandatory artefact floor by software class
R = required, C = conditional as stated, N/A = not applicable. Records may be combined; a required record may not be omitted without an approved exception.
Stage | Class 1 | Class 2 | Class 3 | Class 4 | Tailoring floor | Owner | Approval / evidence
Initiation | R-light | R | R | R | C1: purpose, owner, scope, risk class and disposal date. C2-4: request/charter, feasibility, stakeholders, scope and risk. | Sponsor / delivery lead | G0 decision
Requirements | C | R | R | R | C1: acceptance note; full requirements when user-facing, integrated or persistent data is used. C2-4: requirements/backlog, acceptance, data classification and traceability. | Product owner / analyst | G1 baseline
Design | C | R-proportionate | R | R + independent review | C1: design note for material interface, data or security risk. C2: architecture and test/deployment design. C3-4: add threat/privacy and specialist assurance. | Technical lead | G2 review
Implementation | R-light | R | R | R | Controlled source/configuration, review evidence, build/CI results and component inventory. C1 may use simplified review evidence but must retain source control and basic testing. | Technical lead | G3 code-complete record
Testing | R-basic | R | R + independent QA | R + independent/specialist QA | C1: basic acceptance and defect record. C2-4: plan, cases, results, defects, security/privacy and user acceptance at class depth. | QA lead / product owner | G4 recommendation
Release | C - non-production only | R | R | R | C1: demonstration/non-production release record only; any production use requires reclassification. C2-4: release notes, approval, migration, deployment, rollback and validation. | Release / service owner | G4 authorisation and deployment record
Operations | N/A - production prohibited | R | R | R | C2-4: runbooks, monitoring, access, backup/recovery, support, incidents, targets and reviews. A Class 1 experiment must be reclassified before operational reliance. | Service owner | G5 acceptance and service reviews
Closure | R | R | R | R | C1: disposal date, access removal and data/code disposition. C2-4: acceptance/closure, data disposition, decommissioning, archive and lessons. | Sponsor / service owner | G6 decision

## Framework Alignment
Appendix I - project and software framework reconciliation
Evidence is created once and referenced by both tracks. The higher classification, stronger control and more senior approver govern wherever the mappings differ.
Project gate | Software checkpoint | Consolidation rule
Gate 1 - Intake | G0 - Intake | Use one intake record, sponsor, feasibility screen and initial classification decision.
Gate 2 - Project Authorisation | G1 - Requirements Baseline | Combine when requirements and acceptance criteria are sufficiently mature. If G1 follows later, reuse the charter and add only the requirements evidence; do not repeat the business decision.
Gate 3 - Delivery Readiness | G2 - Design Readiness | Use one integrated readiness pack covering project baseline, architecture, security/privacy, test, deployment, assurance and operational plans.
Gate 4 - Release Readiness | G3 prerequisite and G4 - Release Readiness | G3 code-complete evidence is an engineering prerequisite. One G4/Gate 4 approval pack authorises release under the stricter approver set.
Gate 5 - Continuation / Exception | G3 or G5 evidence where relevant | Gate 5 is recurring or triggered project governance. Engineering or early-life evidence may support it; no duplicate gate is required solely because numbering differs.
Gate 6 - Closure | G5 - Operational Acceptance and G6 - Retirement/Closure | Use G5 evidence for handover. Use G6 when the project closes or a service is retired. One closure record may satisfy both where scope matches.
Gate 7 - Benefits | Post-implementation review evidence; no separate software gate | Use service measures and the software review as evidence for the single Gate 7 benefits decision.
Classification mapping
Project class | Normal software class | Mandatory interpretation
Class C - Small / Low Risk | Software Class 1 or Class 2 | Class 1 is permitted only for time-bound, non-production experimentation with no real personal, client-confidential or payment data. Any operational or production use is at least Class 2.
Class B - Standard / Medium Risk | Software Class 2 or Class 3 | Use Class 3 where personal/sensitive data, public exposure, finance/identity, material reputation, contractual service levels or significant recovery impact exists.
Class A - Strategic / High Risk | Software Class 3 or Class 4 | Use Class 4 for safety-significant, critical-infrastructure, large-scale restricted-data or mission-critical services. Executive governance and explicit residual-risk acceptance apply.

## Risk and Issue Register
Risk and Issue Register
Use the form: Because of [cause], there is a possibility that [uncertain event], resulting in [effect on objectives]. For issues, state what has happened, current impact, immediate containment, root-cause owner and resolution date.
ID | Risk or issue statement | Type | Category | Likelihood | Impact | Rating | Owner | Response | Action | Due | Residual risk | Status | Last review | Next review
R-001 | Because the bank API sandbox has no certification slot before November, there is a possibility that connectivity testing slips, resulting in a Gate 4 delay | Risk | Technical | Medium | High | High | Technical Lead | Reduce | Book a certification slot and prepare an aggregator fallback path | 2026-10-15 | Moderate | Open | 2026-09-15 | 2026-09-29
Row 5 is a worked example. Delete it or keep it below your live entries.

## Change Requests
Change Requests
A change becomes part of the project only after need, impact, alternatives, risks, cost, schedule, quality and benefits are assessed and the correct authority approves it.
Change ID | Date | Requester | Requested change and reason | Urgency and consequence of delay | Scope and requirements impact | Schedule and milestone impact | Cost, resources and procurement impact | Quality, security, privacy and operational impact | Risk, benefit and stakeholder impact | Options considered | Recommendation | Decision and conditions | Change authority | Baselines updated by | Implementation verified
CR-001 | 2026-09-20 | Product Owner | Add multi-currency display conversion to the first release | Medium - client demonstration on 12 November | Adds 3 requirements and 2 acceptance criteria | +5 business days on the build milestone | +GHS 4,000 contractor effort | Adds an exchange-rate dependency requiring availability monitoring | Improves client acceptance likelihood; adds a third-party dependency risk | Reject / defer / substitute / reduce other scope / approve | Approve with a rate-provider fallback | Approved with conditions | Project Sponsor | Project Manager | Pending
Row 5 is a worked example. Delete it or keep it below your live entries.

## Exceptions
Exceptions
Types: Exception (approved, time-bound deviation) or Non-conformance (required process or evidence absent, inaccurate or bypassed). An expired exception is non-compliance. An exception may never authorise unlawful conduct. Critical non-conformance blocks the relevant gate.
Exception ID | Date raised | Type | Exact requirement that cannot be met | Business and technical reason | Affected systems, data, users | Duration | Risk assessment | Accountable risk owner | Compensating controls | Validation evidence | Remediation plan and owner | Expiry date | Approval level and approver | Status
EX-001 | 2026-09-22 | Exception | Independent QA for a Class 3 release (Appendix A testing floor) | No second qualified tester available in the delivery window | Bank connectivity module; no personal data in test | Until 2026-11-30 | Moderate residual risk of undetected regression | Technical Lead | External reviewer appointed for regression evidence; extended smoke test set | Reviewer report and test results attached | Recruit or contract a QA reviewer before the next release - Delivery Lead | 2026-11-30 | Project Authority | Open
Row 5 is a worked example. Delete it or keep it below your live entries.

## Emergency Changes
Emergency Changes
Software, production-service or client-data emergencies follow the SDLC emergency-change procedure: named authority and deputy, non-waivable minimum record, deferrable-evidence list and a retrospective review within 72 hours of stabilisation. All other projects: Sponsor records the same elements and convenes a review within 5 business days.
Emergency ID | Incident / change identifier | Date and time | Requester | Authoriser | Operator | Reason (contain / restore / prevent harm / urgent security) | Scope | Least-privileged access used | Activity logs protected | Backup taken or reason unsafe | Rollback or containment path | Smoke / safety verification | Deferred evidence and owners | Due dates | Retrospective review date | Review outcome | Repeat? Problem record raised
EM-001 | INC-2026-041 | 2026-11-04 22:10 | On-call engineer | Service Owner | DevOps engineer | Restore a failed service | Payments read API pod restart and config rollback | Yes | Yes | Yes - snapshot 22:05 | Revert to build 1.4.2 | Smoke suite passed 22:35 | Full regression pack; final release notes | 2026-11-07 | 2026-11-06 | Change retained; root cause assigned | No
Row 5 is a worked example. Delete it or keep it below your live entries.

## Decision Log
Decision Log
Gate decisions are one of: Approve, Approve with conditions, Hold, Redirect, Terminate. Unresolved critical conditions cannot be treated as 'approve with conditions'.
Decision ID | Date | Gate or trigger | Decision requested | Authority | Evidence reviewed | Decision | Conditions | Dissent recorded | Condition owner | Condition due date | Status
D-001 | 2026-09-30 | Gate 3 / G2 | Approve baselines and authorise execution | Project Sponsor | Integrated plan, architecture, threat model, test strategy, benefits funding | Approve with conditions | Confirm the QA reviewer before the first build increment | None | Delivery Lead | 2026-10-10 | Open
Row 5 is a worked example. Delete it or keep it below your live entries.

## Measures
Year-One mandatory measurement set
Both frameworks make five measures mandatory from the effective date of 31 October 2026. Record the current value at the stated frequency.
Track | Measure and calculation | Source / owner | Frequency | Year-One target | Current value | As at date
PM | Milestone reliability = milestones achieved on or before the approved date / milestones due | Approved schedule and status reports / Project Manager; consolidated by Framework Owner | Monthly | At least 85% portfolio-wide
PM | Absolute cost forecast variance = ¦forecast total cost - approved budget¦ / approved budget | Budget, commitments and forecast / Project Manager and Finance | Monthly | Within class tolerance: A 5%, B 10%, C 15%
PM | First-pass acceptance rate = deliverables accepted without material rework / deliverables presented | Acceptance and defect records / Quality Reviewer or acceptance authority | At each acceptance event; quarterly portfolio total | At least 90%
PM | Overdue critical risk actions = count of critical-risk actions past their approved due date | Risk register / Project Manager; challenged by Assurance | Weekly on project; monthly portfolio total | Zero overdue critical actions
PM | On-time Gate 7 completion = Gate 7 decisions completed by due date / Gate 7 reviews due | Project register and benefits records / Framework Owner and Sponsor | Monthly tracking; quarterly report | 100% completed on time
SDLC | Delivery flow: median lead time from authorised work item to accepted release, with material delay reasons | Delivery lead | Monthly | Set by project; trend must not deteriorate
SDLC | Defect escape rate = production defects / total defects found in testing and production, reported with severity | QA lead | Per release and quarterly | Set by project; severity trend reported
SDLC | Availability: observed production-service availability against the approved service target | Service owner | Monthly | Approved service target
SDLC | Open vulnerability age by severity against institutional service targets | Technical / security owner | Monthly | Within the Class service targets
SDLC | Gate compliance = applicable gates with required evidence and approval recorded before the governed commitment | Freston Kenny Adedeme, Framework Owner | Quarterly | 100%