INSTITUTIONAL GOVERNANCE FRAMEWORK

Project Management Framework

Lifecycle, Governance, Controls and Practical Templates

KenAddme IT Links

Document status: Approved for Use. Approved on 2 September 2026 and effective from 31 October 2026. Document owner and custodian: Freston Kenny Adedeme.

Version 1.1  |  September 2026

Prepared for management, project sponsors, project managers, technical teams, quality reviewers and partners

# Document Control

| Field | Details |
| --- | --- |
| Document title | KenAddme IT Links Project Management Framework |
| Document owner and custodian | Freston Kenny Adedeme |
| Version | 1.1 |
| Status | Approved for Use |
| Approval date | 2 September 2026 |
| Effective date | 31 October 2026 |
| Transition period | From approval on 2 September 2026 through 30 October 2026; full compliance is mandatory from the effective date of 31 October 2026 |
| Review cycle | Annually, or earlier after a major organisational, legal, technology or risk change |
| Applies to | All internal, client, research, software, infrastructure, training, consultancy and transformation projects |
| Classification | Internal governance document |
| Ownership notice | Owned by Freston Kenny Adedeme and authorised for institutional use by KenAddme IT Links. |

## Approval Record

| Role | Name | Decision | Signature | Date |
| --- | --- | --- | --- | --- |
| Document Owner / Approving Authority | Freston Kenny Adedeme | Approved for institutional use | Electronic approval recorded | 2 September 2026 |
| Framework Custodian | Freston Kenny Adedeme | Ownership and maintenance accepted | Electronic record | 2 September 2026 |
| Independent Review Basis | Editorial and governance review | Eleven findings accepted and closed | Review record retained | 1-2 September 2026 |
| Institutional User | KenAddme IT Links | Mandatory from effective date | Controlled electronic copy | 31 October 2026 |

## Revision History

| Version | Date | Summary of change | Author / Owner |
| --- | --- | --- | --- |
| 1.0-draft | 1 September 2026 | Initial institutional framework submitted for independent editorial and governance review. | KenAddme IT Links |
| 1.0 | 2 September 2026 | All eleven pre-approval findings closed; framework approved for institutional use. | Freston Kenny Adedeme |
| 1.1 | 2 September 2026 | Closure verification corrections applied (N1-N7): Gate 1 authority proportioned by class, reconciliation version reference made edition-neutral, emergency-change depth aligned with the Software Development and Engineering Framework, transition window and versioning convention stated, Project Authority quorum fallback added, and release authority defined. | Freston Kenny Adedeme |

## Approval Basis and Findings Closure

Approval basis: The independent review dated 1 September 2026 recommended approval subject to correction. Findings 1-11 have all been incorporated in this controlled edition; none is deferred to a later release. A closure verification dated 2 September 2026 confirmed all eleven closures and raised seven consequential items (N1-N7); those corrections are incorporated in Version 1.1 and are summarised in the revision history.

| # | Severity | Finding | Closure incorporated in Version 1.0 |
| --- | --- | --- | --- |
| 1 | S2 | Project and software frameworks did not reconcile. | Appendix I now maps classification, gates, roles and the common effective date; evidence is produced once and relied upon by both frameworks. |
| 2 | S2 | No default tolerances or financial authority thresholds. | Sections 3.1-3.2 establish class tolerances and binding interim GHS approval bands. |
| 3 | S2 | Role separation had no minimum floor. | Section 3.3 prohibits self-approval and specifies compensating independent assurance. |
| 4 | S2 | The Project Authority was not constituted. | Section 3.4 defines membership, quorum, cadence, powers and the sponsor-conflict rule. |
| 5 | S3 | Monitoring appeared sequential and Gate 5 was untriggered. | Section 8 makes monitoring continuous and assigns class-based reporting and Gate 5 cadence plus event triggers. |
| 6 | S3 | Benefits review had no enforcement mechanism. | Section 10 sets default due dates, funded effort, register status and overdue reporting. |
| 7 | S3 | No expedited initiation path existed. | Section 4.6 creates a constrained combined Gate 1/2 path with deadlines and retrospective review. |
| 8 | S3 | The responsibility matrix assigned more than one accountable party. | Appendix H now gives one accountable authority per activity and separates threshold-dependent decisions. |
| 9 | S4 | No records retention schedule existed. | Section 16.4 and Appendix J establish default retention, legal-hold and secure-disposal rules. |
| 10 | S4 | No Ghanaian legal or regulatory baseline existed. | Authority and Interpretation now names the applicable Ghanaian statutory baseline and official reference points. |
| 11 | S4 | Performance measures were undefined and unowned. | Section 18.1 now defines five mandatory Year-One measures, sources, owners, frequency and targets. |

## Authority and Interpretation

This framework establishes the minimum project-management controls required at KenAddme IT Links. Project-specific plans may introduce stronger controls, but they must not remove mandatory approvals, accountability, evidence, security, financial or quality requirements without an authorised, lawful and time-bound exception. Where a client contract, law, regulator, funder or approved institutional policy imposes a higher requirement, the higher requirement takes priority.

Ghanaian compliance baseline: Projects involving personal data must assess and comply with the Data Protection Act, 2012 (Act 843). Projects delivering or affecting cybersecurity services must assess the Cybersecurity Act, 2020 (Act 1038). Publicly funded bids or delivery must consider the Public Procurement Act, 2003 (Act 663), as amended by Act 914, and current Public Procurement Authority instruments. The sponsor must obtain qualified advice where applicability or obligations are uncertain.

Official reference points current at approval: Data Protection Commission - https://dataprotection.org.gh/; Cyber Security Authority - https://www.csa.gov.gh/resources.php; Public Procurement Authority - https://ppa.gov.gh/online-documents/public-procurement-act/. These references are a governance baseline and do not replace legal advice.

# Executive Summary

Projects succeed when the institution makes the right investment decisions, defines the intended outcome, plans realistically, controls delivery, accepts evidence-based results and learns from completion. This framework converts those expectations into a consistent operating system for KenAddme IT Links.

Core rule: No project moves to the next stage merely because work has started. It moves only when the required evidence is complete, risks are understood, responsible leaders approve the decision and the next stage is resourced.

The lifecycle contains seven governance stages: strategic intake, initiation and feasibility, detailed planning, execution, continuous monitoring and control, transition and closure, and post-project benefits review. Stage 5 is a recurring control cycle that begins when execution is authorised; it is not work postponed until Stage 4 ends. Each gate decision is recorded as approve, approve with conditions, hold for correction, redirect, or terminate.

The framework also defines project classes, decision rights, key records, control disciplines, escalation rules, performance indicators and reusable templates. It is designed to be tailored: a small internal task should not carry the same paperwork as a high-risk client platform, but every project must still have an owner, objective, scope, plan, risk view, acceptance evidence and closure record.

Software projects: A software project must comply with this framework and the KenAddme IT Links Software Development and Engineering Framework. Appendix I consolidates their classes, gates and roles so a single evidence pack and decision may satisfy both where the conditions align.

## The Seven Institutional Stages

| Stage | Primary question | Mandatory decision |
| --- | --- | --- |
| 1. Strategic Intake | Should KenAddme invest attention in this idea? | Authorise feasibility work or decline. |
| 2. Initiation and Feasibility | Is the proposed project viable and worthwhile? | Approve the project charter and sponsor. |
| 3. Detailed Planning | Can the work be delivered responsibly? | Approve baselines and authorise execution. |
| 4. Execution | Are approved deliverables being produced? | Accept work packages and continue delivery. |
| 5. Continuous Monitoring and Control | Is performance within approved tolerances at the required cadence or after a trigger? | Continue, correct, rebaseline, escalate or stop. |
| 6. Transition and Closure | Has the outcome been accepted and safely handed over? | Approve closure and release resources. |
| 7. Benefits Review | Did the project create the intended value? | Confirm benefits, corrective actions and lessons. |

# 1. Purpose, Scope and Principles

## 1.1 Purpose

The purpose of this framework is to provide KenAddme IT Links with one clear method for selecting, planning, delivering, controlling and closing projects. It supports better decisions, reduces avoidable failure, protects institutional resources, improves client confidence and preserves reliable evidence for future learning.

## 1.2 Scope

The framework applies from the first recorded idea through benefits review. It covers internal improvement projects, software and digital products, data and AI work, infrastructure, cybersecurity, training, research, consultancy, client implementation and partnership projects. Routine operational work may use lighter controls unless it creates a defined temporary effort, special risk, material cost or a unique deliverable; in those cases it should be managed as a project.

## 1.3 Project Definition

A project is a temporary, authorised effort undertaken to create a unique product, service, capability or result. It has a defined purpose, accountable owner, start and end boundaries, resources, risks and acceptance conditions. Repetitive ongoing work belongs to operations, although an operational improvement initiative may itself be a project.

## 1.4 Institutional Principles

- Value before activity. Projects must solve a real problem or create a defined opportunity.

- One accountable sponsor. Every project must have an authorised business owner who remains accountable for value and major decisions.

- Evidence before approval. Important decisions must be supported by documented facts, assumptions, estimates, risks and acceptance evidence.

- Realistic commitment. Scope, time, cost, quality and resources must be balanced; leadership must not approve mutually impossible expectations.

- Security, privacy and ethics by design. Controls are planned from the beginning and verified before release.

- Controlled change. Changes are assessed and authorised before becoming part of the baseline.

- Transparent reporting. Problems are reported early, accurately and without concealment.

- Fit-for-purpose governance. Control effort is proportional to project size, complexity and risk.

- Learning and accountability. Closure includes lessons, ownership transfer and review of intended benefits.

# 2. Project Classification and Tailoring

Classification determines the minimum level of governance. The project manager proposes a class during intake. The Sponsor confirms a Class C classification; the Project Authority confirms Class A and Class B and ratifies Class C intakes in batch at its monthly review. Appendix A states the matching Gate 1 decision authority. A project moves to the higher class whenever uncertainty exists or when one high-impact condition is present.

| Class | Typical characteristics | Minimum governance |
| --- | --- | --- |
| Class A - Strategic / High Risk | High financial exposure; sensitive or personal data; critical client service; major cybersecurity, legal, safety, AI, infrastructure or reputational risk; several teams or vendors. | Full lifecycle, steering oversight, independent assurance, formal baselines, monthly or more frequent gate reviews, controlled release and benefits review. |
| Class B - Standard / Medium Risk | Defined client or internal project with moderate cost, multiple contributors, technical dependencies or meaningful service impact. | Full lifecycle with proportionate documents, sponsor gates, regular status reporting, risk and change control, acceptance and closure. |
| Class C - Small / Low Risk | Short duration, low cost, limited users, reversible change, one team and low data/security exposure. | One-page charter, simple plan, named owner, risk checklist, acceptance evidence and closure note. |

## 2.1 Classification Factors

- Financial exposure and the cost of failure.

- Number and importance of users, clients and affected services.

- Sensitivity of data, security requirements and privacy impact.

- Technical novelty, integration complexity and dependence on third parties.

- Legal, contractual, regulatory, ethical, safety and reputational exposure.

- Schedule urgency, resource scarcity and difficulty of reversing the outcome.

- Use of artificial intelligence, automated decisions or unproven technology.

## 2.2 Tailoring Rules

Tailoring reduces unnecessary administration while preserving control. The project manager records which documents, meetings and assurance steps will be combined, simplified or expanded. Mandatory items that cannot be removed are: sponsor, objective, scope, classification, schedule, cost/resource view, risk assessment, change authority, security/privacy review where relevant, acceptance criteria, closure and benefits ownership.

Tailoring test: If a missing control would prevent leadership from knowing what is being approved, who is accountable, what could go wrong, what success means or whether the result was accepted, that control may not be removed.

# 3. Governance Structure and Responsibilities

Governance separates ownership, delivery, assurance and acceptance. One person may perform several roles on a small project, but the responsibilities and decision rights must remain clear.

| Role | Primary accountability | Key decisions |
| --- | --- | --- |
| Executive / Project Authority | Institutional priority, funding limits, strategic alignment and major exception decisions. | Approve strategic/high-risk starts, major rebaseline, suspension or termination. |
| Project Sponsor | Business case, intended benefits, priority, resources and final business acceptance. | Approve charter, plan, material changes, stage gates and closure. |
| Project Manager | Integrated planning, coordination, controls, reporting, issue resolution and records. | Manage within approved tolerance; escalate exceptions. |
| Product / Business Owner | User needs, requirements, prioritisation and operational readiness. | Prioritise scope and accept functional outcomes within authority. |
| Technical Lead | Architecture, engineering approach, technical quality, maintainability and technical risk. | Approve technical design and readiness evidence. |
| Quality / Assurance Reviewer | Independent check that process, evidence, tests and gate conditions are reliable. | Recommend pass, conditional pass, hold or reject. |
| Finance / Administration | Budget controls, procurement compliance, payments and financial reporting. | Verify funding, commitments and financial closure. |
| Security / Privacy Reviewer | Security, data protection, access, threat and release controls where applicable. | Approve or block risk-sensitive release conditions. |
| Service / Operations Owner | Operational ownership, support, service levels, monitoring, continuity and benefits evidence after handover. | Accept operational handover, own service risk and convene benefits evidence. |
| Project Team | Produce deliverables, estimates, evidence and timely issue updates. | Complete assigned work within approved standards. |
| Users / Client Representatives | Operational needs, usability feedback, validation and acceptance participation. | Confirm user acceptance according to agreed criteria. |

## 3.1 Decision Rights and Default Tolerances

The approved plan must define tolerances for time, cost, scope, quality and risk. A gate may approve tighter limits, but it may exceed the institutional defaults below only when the Project Authority records the reason, compensating controls and expiry or review date. Forecast breach, critical risk, unauthorised data use, security compromise, contractual failure or inability to meet acceptance criteria must be escalated immediately rather than waiting for the next report.

| Class | Cost tolerance | Schedule tolerance | Scope, quality and risk floor |
| --- | --- | --- | --- |
| Class A | Maximum +/-5% of approved cost baseline. | Maximum +/-5% of approved stage or completion baseline. | Zero tolerance for reduced acceptance criteria, unapproved material scope change, unresolved critical defect, unlawful processing or unaccepted critical risk. |
| Class B | Maximum +/-10% of approved cost baseline. | Maximum +/-10% of approved stage or completion baseline. | Sponsor approval is required for changes affecting benefits, acceptance, security/privacy, contract or material user impact. |
| Class C | Maximum +/-15% of approved cost baseline. | Maximum +/-15% of approved completion baseline. | Any change to the objective, acceptance criteria, production use, personal-data exposure or risk class requires sponsor approval and reclassification review. |

Non-waivable tolerance: There is no tolerance for fraud, deliberate concealment, unlawful activity, unsafe work, unauthorised access, falsified evidence or bypass of a mandatory security, privacy, acceptance or financial control.

## 3.2 Delegated Financial Authority

The following interim institutional bands apply unless a stricter written delegation, client contract or law governs. Amounts are total committed value in Ghana cedis, including taxes, fees, renewals and foreseeable extensions. Commitments must not be split to avoid a band.

| Commitment value / condition | Accountable approval | Mandatory control |
| --- | --- | --- |
| Up to GHS 2,500 within an approved budget line | Project Manager | Finance verifies budget availability and procurement evidence before commitment. |
| GHS 2,501-15,000 | Project Sponsor | Finance concurrence and written commitment record. |
| GHS 15,001-50,000 | Project Authority | Sponsor recommendation, Finance concurrence and documented value/selection decision. |
| Above GHS 50,000; multi-year, foreign-currency, debt, guarantee or material liability | Executive / Project Authority | Finance concurrence and legal/commercial review where relevant. |
| Any unbudgeted commitment or forecast total above the approved baseline | Next higher authority than the normal value band | Approved change request and updated cost forecast before commitment, except authorised emergency containment. |

Freston Kenny Adedeme, as Framework Owner, must review these interim bands using actual cost and delegation evidence by 31 January 2027. A replacement schedule becomes effective only through a controlled revision approved at the same or higher authority level.

## 3.3 Minimum Role Separation

No project manager may approve their own charter, baseline, material change, release, acceptance or closure. For Class A and Class B projects, the sponsor and final acceptance authority must be different people, and no individual may be the sole author, reviewer, tester and approver of the same material deliverable. Class C may combine sponsor and acceptance authority only when the project manager is different and objective acceptance evidence is retained.

Compensating assurance: Where staffing prevents the required separation, the Project Authority must approve a named reviewer who is independent of delivery, the evidence to be checked and the time limit. Class A compensating arrangements require Executive Authority approval and may not waive legal, security, privacy or financial controls.

## 3.4 Constitution of the Project Authority

The KenAddme IT Links Project Authority is the standing governance body for portfolio priority, Class A oversight, major commitments and exceptions. It is chaired by Freston Kenny Adedeme as Document Owner / Executive Authority, or by a formally recorded delegate.

| Element | Institutional rule |
| --- | --- |
| Core membership | Chair/Executive Authority, the relevant Project Sponsor, Finance/Administration and one Technical, Quality, Security or Service representative appropriate to the decision. |
| Quorum | At least three people: the Chair or delegate, the Sponsor, and one control reviewer independent of the Project Manager. The Project Manager may present but does not vote on self-prepared approvals. Where internal staffing cannot supply an independent control reviewer, the Chair may appoint a suitably qualified external reviewer or, with client agreement, a client-side representative to serve for quorum purposes; the appointment, its scope, its independence basis and its time limit must be recorded. This fallback may not be used to satisfy a legal, security, privacy or financial control that requires a specific approver. |
| Cadence | Monthly portfolio and Class A review; ad hoc meetings within two business days for urgent initiation, red status, major exception or termination decisions. |
| Powers | Prioritise intake, confirm classification, approve Class A gates, commitments beyond sponsor limits, material rebaselines, compensating assurance, suspension, termination and framework exceptions. |
| Records | Agenda, attendees, conflicts, evidence reviewed, decision, conditions, dissent, owner and due date must be recorded in the project repository. |
| Sponsor also holds authority role | The Sponsor must not count twice toward quorum. Another management member chairs that decision and an independent control reviewer must concur. |

## 3.5 Gate Decisions

- Approve: all mandatory conditions are satisfied.

- Approve with conditions: limited conditions are assigned with owners and deadlines; unresolved critical conditions cannot be treated this way.

- Hold: evidence or readiness is insufficient and work must pause at the gate.

- Redirect: the objective, approach, scope or solution must be revised before reconsideration.

- Terminate: the project is no longer viable, valuable, lawful, safe or strategically justified.

# 4. Stage 1 - Strategic Intake and Opportunity Definition

## 4.1 Purpose

Strategic intake prevents the institution from spending effort on unclear or low-value ideas. It records the problem, desired outcome, likely beneficiaries, urgency and initial constraints before detailed analysis begins.

## 4.2 Entry Conditions

- A problem, opportunity, client request or improvement idea has been identified.

- A person is willing to act as the idea owner.

- The idea is sufficiently clear to describe in plain language.

## 4.3 Required Activities

- Describe the current situation and the evidence that a problem or opportunity exists.

- Identify affected users, clients, services and institutional goals.

- State the expected outcome without assuming a solution too early.

- Screen for obvious legal, ethical, security, privacy, safety, financial and reputational concerns.

- Estimate urgency, rough scale and whether the work is a project or routine operation.

- Compare the idea with active commitments and resource capacity.

## 4.4 Required Outputs

| Output | Minimum content |
| --- | --- |
| Project Idea / Intake Record | Problem or opportunity, proposed outcome, beneficiaries, owner, urgency and known constraints. |
| Initial Classification | Proposed Class A, B or C with reasons. |
| Initial Screening | Major concerns, dependencies, conflicts and obvious disqualifiers. |
| Portfolio Recommendation | Proceed to feasibility, defer, merge, return for clarification or decline. |

## 4.5 Gate 1 - Intake Decision

Exit criteria: The need is real enough to investigate, an idea owner is identified, the work supports institutional or client value, and feasibility effort is justified.

## 4.6 Expedited Initiation for Urgent Work

A combined Gate 1/2 decision may be used only when delaying a genuinely urgent new project would create material client, security, legal, service, funding or tender harm. Urgency caused solely by poor planning does not qualify. The expedited decision authorises a limited start; it does not waive finance, procurement, security, privacy, safety, acceptance or evidence controls.

| Control | Mandatory expedited-start rule |
| --- | --- |
| Authority | Class B or C requires the Sponsor and Project Authority Chair. Class A requires the Executive / Project Authority and an independent control reviewer. |
| Minimum decision record | Urgent need, objective, provisional scope, sponsor, project manager, class, maximum spend, time limit, principal risks, data/security conditions, acceptance concept and stop authority. |
| Baseline deadline | Class A must present Gate 3 within 5 business days. Class B/C must present Gate 3 within 10 business days. All classes must do so before production release or 25% of authorised budget is committed, whichever occurs first. |
| Retrospective review | The Project Authority reviews necessity, authority, decisions, spend, risk and missing evidence within 5 business days of the start. |
| Failure to regularise | Work is held, commitments stop and the matter is escalated unless the Executive Authority records a lawful, time-bound extension. |

# 5. Stage 2 - Initiation and Feasibility

## 5.1 Purpose

Initiation converts an accepted idea into an authorised project proposal. Feasibility determines whether KenAddme IT Links can and should deliver it under realistic technical, operational, economic, schedule, legal and risk conditions.

## 5.2 Feasibility Dimensions

| Dimension | Questions to answer |
| --- | --- |
| Strategic | Does the project support institutional direction or a valid client commitment? |
| Technical | Can the solution be built, integrated, secured, tested, operated and maintained? |
| Operational | Will users, processes, support teams and infrastructure be ready? |
| Economic | Are total costs justified by expected value and available funding? |
| Schedule | Can the outcome be delivered by the needed date with realistic dependencies? |
| Legal / Contractual | Are rights, obligations, licences, data uses and vendor terms acceptable? |
| Ethical / Social | Could the project create unfair, harmful or inappropriate outcomes? |
| Resource | Are suitable people, tools, environments and suppliers available? |

## 5.3 Required Activities

- Identify alternative approaches, including doing nothing, buying, building, partnering or changing the process.

- Prepare high-level scope, exclusions, assumptions and acceptance concept.

- Estimate cost, duration, resource demand and expected benefits as ranges where uncertainty is high.

- Identify principal risks, dependencies and constraints.

- Nominate sponsor, project manager and key decision makers.

- Prepare a project charter and proportionate business case.

## 5.4 Gate 2 - Project Authorisation

Exit criteria: A sponsor accepts accountability; the business case is credible; scope and intended outcome are clear; major risks are understood; suitable resources are likely available; and feasibility evidence supports proceeding.

# 6. Stage 3 - Detailed Planning and Baseline Approval

## 6.1 Purpose

Planning converts the charter into a coordinated delivery baseline. It defines what will be produced, how work will be organised, when it will happen, who will perform it, what it will cost, how quality will be verified and how risks, changes and communication will be controlled.

## 6.2 The Integrated Project Plan

- Scope statement, deliverables, exclusions, requirements and acceptance criteria.

- Work breakdown structure with manageable work packages.

- Schedule with dependencies, milestones, estimates, critical constraints and contingency.

- Budget, procurement, staff effort, tools, infrastructure and reserves.

- Responsibility assignment and decision authority.

- Quality plan, review points, test strategy and evidence required for acceptance.

- Risk register, response actions, issue process and escalation thresholds.

- Communication, stakeholder engagement and reporting calendar.

- Security, privacy, data, access, backup, continuity and release controls where relevant.

- Change, configuration, version, document and records management.

- Transition, training, support, handover, rollback and closure approach.

- Funded benefits-review effort, operational benefit owner and default Gate 7 due date.

## 6.3 Baseline Quality Tests

| Test | Planning evidence |
| --- | --- |
| Complete | Every approved deliverable appears in the work, schedule, ownership and acceptance plans. |
| Consistent | Scope, schedule, budget, resources and quality expectations do not contradict one another. |
| Achievable | Estimates reflect actual capacity, dependencies, uncertainty and constraints. |
| Controlled | Tolerances, reporting, risks, changes and decisions have named owners and methods. |
| Acceptable | Sponsor, delivery leads, reviewers and affected operational owners agree to their responsibilities. |

## 6.4 Gate 3 - Delivery Readiness

Exit criteria: The integrated plan is realistic; funds and people are committed; key requirements and acceptance criteria are testable; material risks have responses; controls and reporting are ready; and the sponsor formally authorises execution.

# 7. Stage 4 - Execution and Team Coordination

## 7.1 Purpose

Execution produces the approved deliverables and builds readiness for their use. The project manager coordinates people, information, suppliers, decisions and environments so that work is completed according to the baseline and verified progressively.

## 7.2 Required Practices

- Hold a formal kickoff that confirms objectives, roles, ways of working, reporting and escalation.

- Authorise work packages with clear outputs, owners, dates, quality criteria and dependencies.

- Maintain one controlled source for current plans, decisions, risks, issues, changes and deliverable versions.

- Review deliverables early and progressively; do not postpone quality until final testing.

- Manage team capacity, collaboration, knowledge transfer and conflict.

- Control vendors, external contributors and client dependencies against agreed obligations.

- Prepare users, operations, training, support, data migration and release environments in parallel with development.

- Record evidence of reviews, tests, approvals and corrected defects.

## 7.3 Work Package Acceptance

A work package is complete only when its output exists, specified checks have passed, defects are resolved or formally accepted, supporting documentation is updated, dependencies are communicated and the authorised reviewer accepts the result. Percentage-complete estimates alone are not acceptance evidence.

## 7.4 Gate 4 - Major Deliverable or Release Readiness

Exit criteria: The deliverable meets agreed requirements; tests and reviews are evidenced; unresolved defects and risks are within approved limits; operations and users are ready; security and privacy conditions are satisfied; and release or transition authority is granted.

# 8. Stage 5 - Continuous Monitoring, Control and Corrective Action

## 8.1 Purpose

Monitoring and control begin when Gate 3 authorises execution and continue until Gate 6 closure. They run alongside delivery rather than after it. Their purpose is to detect variance early, forecast outcomes, support timely decisions and keep delivery within authorised scope, time, cost, quality and risk tolerances.

## 8.2 Control Cycle

- Measure actual progress, expenditure, quality, risks, issues and resource use.

- Compare actual and forecast performance with approved baselines and tolerances.

- Analyse root causes, consequences and available corrective actions.

- Decide within authority or escalate to the appropriate decision maker.

- Implement approved correction and update affected plans and records.

- Verify whether the correction worked and communicate the outcome.

## 8.3 Minimum Status Report

| Area | Required information |
| --- | --- |
| Overall status | Green, amber or red with a short evidence-based explanation. |
| Achievements | Completed and accepted outputs since the last report. |
| Next period | Planned milestones, decisions and dependencies. |
| Schedule | Actual and forecast milestones; material variance and cause. |
| Cost / Resources | Spend, commitments, forecast, capacity and variance. |
| Scope / Quality | Approved changes, defects, acceptance and quality trend. |
| Risks / Issues | Top exposures, owners, actions, dates and escalation needs. |
| Decisions | Specific decisions required, decision owner and needed date. |

## 8.4 Required Reporting and Gate 5 Cadence

| Class | Routine status rhythm | Gate 5 decision rhythm |
| --- | --- | --- |
| Class A | Weekly delivery review and formal status at least every two weeks. | Monthly Project Authority continuation review, at every major milestone and immediately after any trigger. |
| Class B | Formal status at least monthly, with team review at least every two weeks. | At least every eight weeks, at every major milestone and immediately after any trigger. |
| Class C | Status at least monthly while active; a midpoint check is required when duration exceeds 20 business days. | At midpoint for projects longer than 20 business days and immediately after any trigger. |

A Gate 5 trigger occurs when Section 12.2 requires immediate escalation; a tolerance is forecast to be breached; a material change, rebaseline, funding release, supplier failure or recovery plan needs approval; a critical dependency changes; acceptance becomes doubtful; or the Sponsor, Project Authority or assurance reviewer calls the gate. The project manager must convene the decision within two business days for a red condition and within five business days for any other material trigger.

## 8.5 Gate 5 - Continuation or Exception Decision

Exit criteria: Forecast performance remains acceptable, or a credible recovery/rebaseline decision has been approved. If value has disappeared, risk is unacceptable or recovery is not credible, the project must be paused, redirected or terminated.

# 9. Stage 6 - Transition, Acceptance and Closure

## 9.1 Purpose

Closure is a controlled transfer of responsibility, not simply the end of team activity. It confirms that deliverables are accepted, operations can support them, obligations are settled, records are preserved and remaining work has an accountable owner.

## 9.2 Closure Requirements

- Obtain formal acceptance against approved criteria and record any accepted limitations.

- Complete release, migration, training, support, security, backup, recovery and operational-readiness actions.

- Transfer ownership of products, data, licences, environments, documentation and unresolved actions.

- Close or hand over contracts, invoices, assets, accounts and access rights.

- Reconcile the budget and record final cost, schedule, scope and quality performance.

- Archive current versions, approvals, evidence, decisions, lessons and closure records.

- Release people and resources responsibly and acknowledge contributions.

- Assign benefits measures, owners, review dates and outstanding corrective actions.

## 9.3 Gate 6 - Closure Approval

Exit criteria: The authorised client or sponsor has accepted the outcome; operations own it; outstanding actions are assigned; finances and contracts are reconciled; records are archived; and the sponsor approves project closure.

## 9.4 Early Termination

A terminated project still requires controlled closure. The project manager must protect data and assets, stop commitments, settle obligations, preserve useful work, document the decision, capture lessons and transfer any remaining responsibilities.

# 10. Stage 7 - Benefits Realisation and Post-Project Review

## 10.1 Purpose

A deliverable can be completed without creating value. Benefits review examines whether the result is being used, whether the intended improvement occurred, what unintended effects appeared and what further action is required.

## 10.2 Benefits Plan

| Element | Required definition |
| --- | --- |
| Benefit | The measurable improvement expected from the project. |
| Baseline | The situation or performance before implementation. |
| Measure | Indicator, calculation method and data source. |
| Target | Expected amount of improvement and date. |
| Owner | Operational leader accountable after project closure. |
| Dependencies | Conditions outside the project needed to realise value. |
| Review dates | When early, intermediate and final results will be checked. |

## 10.3 Default Timing, Funding and Enforcement

| Class | Default Gate 7 due date | Minimum protected review effort |
| --- | --- | --- |
| Class A | Interim review at 3 months and formal Gate 7 at 6 months after Gate 6; a 12-month review is added where the benefit horizon requires it. | Two person-days plus necessary measurement cost, included in the Gate 3 budget and not released at Gate 6. |
| Class B | Formal Gate 7 at 6 months after Gate 6 unless the approved benefits plan sets an earlier date. | One person-day plus necessary measurement cost, included in the Gate 3 budget. |
| Class C | At 90 days after Gate 6, or at Gate 6 when all benefits are immediately measurable and the Sponsor records the evidence. | At least one-half person-day or equivalent documented effort. |

After Gate 6, the project register status becomes "Operational - Benefits Pending" rather than fully closed. The Service / Operations Owner becomes responsible for evidence and the Sponsor remains accountable for Gate 7. The record changes to "Closed - Benefits Reviewed" only when the Gate 7 decision is recorded. The Framework Owner reviews the register monthly and reports overdue Gate 7 reviews to the Project Authority each quarter. An overdue review is a governance non-conformance and requires a dated corrective action.

## 10.4 Review Questions

- Is the delivered product or capability being used as intended?

- Did service, revenue, efficiency, learning, quality, safety or client outcomes improve?

- Were costs, delays, negative impacts or risks transferred elsewhere?

- Which assumptions were correct or incorrect?

- What corrective actions, follow-on investment or retirement decisions are needed?

- Which lessons should become institutional standards or training content?

## 10.5 Gate 7 - Benefits Confirmation

Exit criteria: Benefits evidence is reviewed, remaining actions have owners, important lessons are incorporated into institutional practice and leadership decides whether to sustain, improve, expand, replace or retire the outcome.

# 11. Core Project Management Disciplines

## 11.1 Integration Management

Maintain one coherent project view. Decisions in scope, schedule, cost, quality, resources, risk and change must be assessed together. The project manager owns the integrated plan and ensures that approved changes update every affected baseline and record.

## 11.2 Scope and Requirements Management

Define what is included, excluded and required. Requirements should be clear, testable, traceable, prioritised and approved. Deliverables must map to acceptance criteria, and unapproved additions must not quietly enter the work.

## 11.3 Schedule Management

Break work into estimable activities, identify dependencies, assign realistic durations and resources, establish milestones and protect contingency. Report forecasts, not only past completion. Critical delays require recovery decisions and updated impact analysis.

## 11.4 Cost and Resource Management

Estimate total ownership cost, not only purchase or development cost. Control labour, procurement, infrastructure, subscriptions, travel, support and reserves. Commitments and forecasts must be visible before funds are exhausted.

## 11.5 Quality Management

Define standards and acceptance evidence before execution. Apply prevention, peer review, testing, inspection, audit and user validation. A completed activity is not a quality result until evidence demonstrates conformity.

## 11.6 Risk and Issue Management

Risk concerns an uncertain future event; an issue has already occurred. Both require owners, consequences, actions and dates. Critical exposures are escalated promptly. Risk reserves and contingency actions must be realistic and authorised.

## 11.7 Stakeholder and Communication Management

Identify those who influence, use, fund, support or are affected by the project. Plan what each group needs to know, decide or contribute. Communication must be timely, truthful, accessible and appropriate to confidentiality.

## 11.8 Procurement and Supplier Management

Define requirements and evaluation criteria before selection. Conduct proportionate due diligence, clarify intellectual property, confidentiality, data handling, service levels, acceptance, payment, exit and continuity obligations.

## 11.9 Security, Privacy and Responsible Technology

Classify information, restrict access, protect credentials, assess threats, minimise data, maintain backups and verify secure release. High-risk automation or AI requires explicit human oversight, evaluation, monitoring and approved use boundaries.

## 11.10 Configuration and Records Management

Control document, code, design, data and release versions. Preserve decision and approval history, define naming and access rules, and ensure the team can identify the authoritative current version.

# 12. Risk, Issue and Escalation Framework

## 12.1 Risk Assessment

Each material risk should state the cause, uncertain event and consequence. Assess likelihood and impact using an agreed scale, identify existing controls, estimate residual exposure and assign a response owner. Responses may avoid, reduce, transfer, share or accept the exposure.

| Rating | Meaning | Required response |
| --- | --- | --- |
| Low | Limited effect; manageable within routine work. | Monitor and manage by the assigned owner. |
| Moderate | Noticeable effect on one or more objectives. | Plan response, review regularly and report trend. |
| High | Serious effect, tolerance breach likely or major dependency. | Sponsor attention, funded response and close monitoring. |
| Critical | Threat to legality, safety, security, viability, reputation or essential service. | Immediate escalation; pause affected work unless authorised safe containment exists. |

## 12.2 Immediate Escalation Triggers

- Actual or suspected security incident, privacy breach, fraud, unlawful activity or serious ethical concern.

- Forecast breach of approved cost, time, scope, quality or risk tolerance.

- Loss of critical sponsor, specialist, supplier, environment, licence or funding.

- Failure that could materially affect a client, public service, institutional reputation or contractual obligation.

- Evidence that acceptance criteria cannot be met under the approved plan.

- Material conflict of interest, falsified evidence or deliberate concealment of project status.

## 12.3 Issue Resolution

Issues are logged with impact, urgency, owner, target date, decisions and status. The owner analyses root cause and options; the project manager coordinates resolution; and unresolved issues cross the escalation threshold based on impact and time, not personal comfort.

# 13. Change and Baseline Control

## 13.1 Change Principle

Change is normal, but uncontrolled change destroys accountability. A request becomes part of the project only after its need, impact, alternatives, risks, cost, schedule, quality and benefits are assessed and the correct authority approves it.

## 13.2 Change Procedure

- Record the request, reason, requester and affected requirement or deliverable.

- Screen urgency and determine whether emergency containment is needed.

- Analyse effects across scope, schedule, cost, resources, quality, security, operations, contracts and benefits.

- Identify options, including reject, defer, substitute, reduce other scope or rebaseline.

- Obtain the decision from the authorised change authority.

- Update baselines, contracts, tasks, risks, acceptance criteria and communications.

- Verify implementation and close the change record with evidence.

## 13.3 Emergency Change

Emergency action may be taken to contain imminent harm, restore service or protect data, but it must remain within authorised emergency procedures. The decision, evidence, affected configuration, residual risk and retrospective approval must be recorded as soon as practicable. An emergency change that affects software, a production service or client data must follow the emergency-change procedure in the Software Development and Engineering Framework, including its named authority and deputy, its non-waivable minimum record, its deferrable-evidence list and its 72-hour retrospective review. For all other projects the Sponsor must record the same elements and convene a retrospective review within five business days of stabilisation. A repeated emergency change for the same condition requires a problem record and a permanently governed correction; emergency authority must not become a routine delivery path.

## 13.4 Rebaselining

A baseline is revised only when the authorised decision changes the agreed future. It must not be rewritten merely to hide past variance. Reports should retain the original commitment, approved changes and current forecast so leadership can understand performance honestly.

# 14. Quality Assurance, Testing and Acceptance

## 14.1 Quality Planning

Quality requirements translate stakeholder expectations into measurable conditions. The quality plan identifies standards, reviewers, methods, environments, evidence, defect thresholds and acceptance authority. High-risk deliverables require reviewers independent enough to challenge the delivery team.

## 14.2 Verification and Validation

| Control | Purpose | Examples |
| --- | --- | --- |
| Verification | Confirm the deliverable was built according to specification. | Peer review, inspection, unit tests, integration tests, security tests, document review. |
| Validation | Confirm the result is suitable for real user and business needs. | User acceptance, pilot, operational rehearsal, client demonstration, benefits test. |
| Assurance | Confirm the process, evidence and decisions are trustworthy. | Gate review, independent audit, traceability check, readiness assessment. |

## 14.3 Acceptance Rules

- Acceptance criteria are approved before final delivery.

- Evidence identifies the deliverable version and test environment.

- Failed criteria are corrected, retested or formally accepted as documented limitations by authorised persons.

- The person accepting the deliverable has the authority and enough evidence to do so.

- Conditional acceptance includes owners, deadlines and consequences for unresolved items.

# 15. Financial, Procurement and Resource Controls

## 15.1 Financial Control

The project budget must separate approved baseline, contingency, management reserve and later changes. Status reporting must show actual expenditure, committed expenditure, forecast to complete and forecast total cost. Commitments and reallocations must follow Section 3.2; a project-specific plan may tighten but may not silently weaken those bands.

## 15.2 Procurement Control

- Document the need, selection criteria, budget and approval before commitment.

- Compare suitable options and record the selection decision and conflicts of interest.

- Use written terms that define scope, deliverables, quality, security, confidentiality, data use, intellectual property, payment, changes, support and exit.

- Verify deliverables and approval evidence before payment.

- Track supplier performance, dependencies, risks, licences and renewal dates.

Publicly funded work: Where KenAddme IT Links bids for or delivers publicly funded work, the Sponsor and Finance/Administration must identify applicable tender, approval, documentation and retention requirements under the Public Procurement Act, 2003 (Act 663), as amended by Act 914, and current Public Procurement Authority instruments. Client procurement rules do not remove KenAddme internal approvals.

## 15.3 Resource Management

Plans must reflect actual availability, skills, competing work, leave, learning needs and transition responsibilities. Over-allocation should be treated as a delivery risk. Critical knowledge should not depend on one person without documentation, pairing, backup or succession action.

# 16. Communication, Documentation and Records

## 16.1 Communication Principles

Communication is planned according to stakeholder influence, interest, decision authority and information need. Reports should distinguish facts, forecasts, assumptions, decisions and requests. Sensitive project information must only reach authorised recipients through approved channels.

## 16.2 Minimum Project Repository

- Approved charter, business case, classification and governance record.

- Requirements, scope, work breakdown, schedule, budget and resource plan.

- Risk, issue, decision, assumption, dependency and change registers.

- Meeting decisions, status reports, approvals and escalation evidence.

- Designs, deliverables, test evidence, acceptance and release records.

- Contracts, procurement records, licences and supplier performance evidence.

- Handover, training, support, closure, lessons and benefits records.

## 16.3 Records Rules

Every controlled record must have a meaningful name, owner, version or date, approval state and access classification. The project manager ensures the authoritative version is identifiable. Records must follow the minimum schedule in Appendix J, together with any longer contractual, legal, funder, dispute or client requirement.

## 16.4 Retention, Legal Hold and Disposal

The Service / Operations Owner and records custodian must review project records at Gate 6 and annually while any retention period remains. Personal data must be minimised, access-restricted and retained only for a documented lawful purpose. When a record reaches its disposal date, the custodian must obtain owner approval, securely destroy the authoritative and working copies, and record what was destroyed, when, by whom and by what method.

Legal hold: A dispute, investigation, audit, incident, regulator request, litigation hold or unresolved contractual claim suspends normal disposal. The hold owner must record its scope and release date. A legal hold does not permit unnecessary access or reuse of personal data.

# 17. Delivery Methods and Lifecycle Tailoring

KenAddme IT Links may use predictive, agile, iterative or hybrid delivery. The method changes how work is organised, but it does not remove governance, accountability, security, quality, financial or acceptance duties.

| Approach | Best suited to | Control emphasis |
| --- | --- | --- |
| Predictive | Stable requirements, physical or infrastructure work, contractual milestones, regulated outputs. | Detailed upfront baseline, formal changes, milestone acceptance. |
| Agile / Iterative | Evolving user needs, digital products, experimentation and frequent feedback. | Prioritised backlog, short cycles, frequent demonstrations, quality built into each increment. |
| Hybrid | Stable governance outcomes with uncertain solution details or mixed workstreams. | Stage gates and funding controls combined with iterative delivery and feedback. |

## 17.1 Agile Governance

In agile delivery, the product backlog does not replace the project charter, budget, risk register, security plan or release approval. Each increment should meet a clear definition of done, include required tests and documentation, and remain traceable to authorised objectives. Scope may be reprioritised within approved boundaries; material changes still require authorised decisions.

## 17.2 Research and Experimental Projects

Research projects should define hypotheses, ethical and data boundaries, reproducibility, success and stop criteria, and the difference between laboratory evidence and production readiness. Experimental results must not be presented as validated operational performance until independent evaluation and release gates are satisfied.

# 18. Performance Measurement and Institutional Reporting

## 18.1 Year-One Mandatory Measurement Set

The following five measures are mandatory from the effective date. The Framework Owner consolidates them across the portfolio and presents the results to the Project Authority each quarter. Project managers and named control owners must maintain the source records at the stated frequency.

| Measure and calculation | Source / owner | Frequency | Year-One target |
| --- | --- | --- | --- |
| Milestone reliability = milestones achieved on or before the approved date divided by milestones due. | Approved schedule and status reports / Project Manager; consolidated by Framework Owner. | Monthly | At least 85% portfolio-wide. |
| Absolute cost forecast variance = absolute difference between forecast total cost and approved budget, divided by approved budget. | Budget, commitments and forecast / Project Manager and Finance. | Monthly | Within class tolerance: A 5%, B 10%, C 15%. |
| First-pass acceptance rate = deliverables accepted without material rework divided by deliverables presented for acceptance. | Acceptance and defect records / Quality Reviewer or acceptance authority. | At each acceptance event; quarterly portfolio total | At least 90%. |
| Overdue critical risk actions = count of critical-risk actions past their approved due date. | Risk register / Project Manager; challenged by Assurance. | Weekly on project; monthly portfolio total | Zero overdue critical actions. |
| On-time Gate 7 completion = Gate 7 decisions completed by the approved due date divided by Gate 7 reviews due. | Project register and benefits records / Framework Owner and Sponsor. | Monthly tracking; quarterly report | 100% completed on time. |

## 18.2 Extended Measurement Catalogue

The measures below are optional extensions selected when they materially improve a project or portfolio decision. Their use must identify a definition, data source, owner, frequency and target in the approved plan.

| Dimension | Optional indicators |
| --- | --- |
| Value | Benefit achieved, client outcome, user adoption, service improvement, strategic contribution. |
| Delivery | Milestone reliability, schedule variance, cost forecast, throughput, dependency performance. |
| Quality | Acceptance pass rate, escaped defects, rework, test coverage, service incidents. |
| Risk | Critical exposure, overdue actions, risk trend, audit findings, security/privacy conditions. |
| Stakeholders | Sponsor confidence, user satisfaction, decision turnaround, communication effectiveness. |
| Capability | Knowledge transfer, documentation completeness, staff growth, supplier performance. |

## 18.3 Status Definitions

| Status | Definition |
| --- | --- |
| Green | Objectives are forecast within approved tolerances; no unresolved condition threatens the stage outcome. |
| Amber | A material concern exists, but a credible and owned recovery action is available within authority or pending timely decision. |
| Red | A tolerance is breached or likely to be breached; value, safety, security, legality, acceptance or viability is materially threatened. |

Status colours must be supported by evidence. A project is not green merely because the team is busy or because a deadline has not yet arrived. Forecasts, dependencies, quality and risks determine status.

# 19. Assurance, Audit and Compliance

## 19.1 Assurance Purpose

Project assurance provides confidence that decisions, plans, evidence and controls are reliable. It should be proportionate to risk and sufficiently independent for the reviewer to challenge assumptions and report concerns without pressure.

## 19.2 Assurance Activities

- Gate readiness review and confirmation of required evidence.

- Traceability from business need to requirements, deliverables, tests and acceptance.

- Review of estimates, resources, dependencies, contracts and risk responses.

- Security, privacy, data, quality and operational-readiness assessment.

- Verification that approved changes are reflected in current baselines.

- Post-release monitoring and benefits-evidence review.

## 19.3 Non-Conformance

A non-conformance is recorded when required process or evidence is absent, inaccurate or bypassed. It should state the requirement, evidence, impact, owner, corrective action and due date. Critical non-conformance blocks the relevant gate unless authorised leadership documents a lawful, safe and time-bound exception.

# 20. Implementation Roadmap for KenAddme IT Links

Adoption is phased so the framework becomes normal practice rather than a document that teams rarely use. The framework is approved on 2 September 2026 and becomes mandatory on the common project/software commencement date of 31 October 2026.

Transition rule: During transition, new projects must be classified and planned under this framework. Existing Class A and B projects adopt it at the next gate or by 31 October 2026, whichever occurs first. Critical security, privacy, financial, incident and escalation controls apply from approval and are not deferred.

| Adoption phase | Institutional action |
| --- | --- |
| Phase 1 - Approve and Assign | Completed: approve the framework; appoint Freston Kenny Adedeme as owner and custodian; constitute the Project Authority; adopt interim authority limits. |
| Phase 2 - Configure Templates | Brand the forms, establish the project register and repository, configure status definitions, risk scale, gates and naming conventions. |
| Phase 3 - Pilot | Apply the framework to one small, one standard and, if available, one high-risk project. Record friction, missing controls and training needs. |
| Phase 4 - Train and Roll Out | Train sponsors, project managers, technical leads, finance, assurance and team members using practical project scenarios. |
| Phase 5 - Measure and Improve | Review gate quality, reporting accuracy, project outcomes, lessons and compliance. Update the framework through controlled revisions. |

## 20.1 Transition Requirements

| Work in progress | Required treatment |
| --- | --- |
| New projects during transition | Classify at intake, use the approved templates and plan for full compliance no later than 31 October 2026. |
| Active Class A projects | Apply critical controls from approval and adopt the complete framework at the next gate or by the effective date, whichever occurs first. |
| Active Class B projects | Adopt at the next gate or by the effective date. Record any missing baseline, acceptance, role-separation or authority control as a corrective action. |
| Active Class C projects | At minimum, confirm sponsor, scope, plan, risk, acceptance and closure records before the effective date or project closure, whichever occurs first. |
| Software projects | Use Appendix I and the approved Software Development and Engineering Framework; one aligned evidence pack may satisfy both frameworks. |
| Unmet transition requirement | Record a time-bound exception with owner, compensating control, approval and expiry. Transition is not a general waiver. |

## 20.2 First 90-Day Priorities

- Confirm named deputies and operational representatives for the Project Authority.

- Create one central project register and controlled document repository.

- Adopt the charter, status report, risk register, change request and closure templates in this framework.

- Classify all active projects and identify missing sponsors, baselines, acceptance criteria and critical risks.

- Run gate-readiness reviews for active Class A and Class B projects.

- Train leaders to distinguish honest amber/red reporting from failure; early escalation should be rewarded, not hidden.

# Appendix A - Stage-Gate Checklist

| Gate | Required evidence | Decision owner |
| --- | --- | --- |
| Gate 1 - Intake | Need/opportunity, owner, beneficiaries, initial screening, classification recommendation. | Sponsor for Class C, ratified in batch at the monthly Project Authority review; Project Authority for Class A and Class B |
| Gate 2 - Authorisation | Charter, business case, feasibility, high-level scope, sponsor, principal risks. | Sponsor for Class B/C; Project Authority for Class A |
| Gate 3 - Delivery Readiness | Integrated plan, baselines, resources, quality, risk, security/privacy, benefits funding and transition plans. | Sponsor for Class B/C; Project Authority for Class A |
| Gate 4 - Release Readiness | Accepted deliverables, test evidence, defect/risk position, operational and user readiness. | Named acceptance authority; Project Authority concurrence for Class A |
| Gate 5 - Continuation / Exception | Current forecast, variance analysis, trigger, corrective plan, change or exception request. | Sponsor within tolerance; Project Authority beyond tolerance or for Class A |
| Gate 6 - Closure | Acceptance, handover, financial/contract closure, archived records, lessons, benefits ownership. | Sponsor |
| Gate 7 - Benefits | Benefits measures, usage evidence, outcomes, unintended effects, follow-on actions and register update. | Sponsor, supported by Service / Operations Owner |

## Standard Gate Questions

- What decision is being requested and who has authority to make it?

- What evidence supports the recommendation?

- Are objectives, scope, assumptions and success criteria still valid?

- Are resources, funding, dependencies and operational ownership adequate?

- Are critical risks, issues, security, privacy, legal and quality conditions acceptable?

- What conditions, actions or limits attach to approval?

- What will cause the project to return, pause, escalate or stop?

# Appendix B - Project Charter Template

| Charter field | Required content |
| --- | --- |
| Project title and ID | Unique name and project-register reference. |
| Sponsor and project manager | Named accountable sponsor and delivery lead. |
| Problem / opportunity | Evidence-based description of the current situation. |
| Purpose and objectives | Specific outcomes the project intends to achieve. |
| Scope and exclusions | What is included and explicitly not included. |
| Key deliverables | Products, services, capabilities or results to be accepted. |
| Success and acceptance criteria | Measurable conditions for completion and value. |
| Stakeholders and users | Main affected or decision-making groups. |
| High-level schedule and budget | Major milestones, expected duration and funding range. |
| Software framework alignment | Software Class 1-4, aligned G0-G6 checkpoints and Appendix I mapping where applicable. |
| Risks, assumptions, constraints | Principal uncertainties and limits. |
| Governance and tolerances | Decision rights, reporting, escalation, role separation, financial band and change authority. |
| Benefits ownership and funding | Operational owner, measures, default Gate 7 date and protected review effort. |
| Approval | Names, decisions, dates and conditions. |

## Charter Approval Statement

By approving this charter, the sponsor authorises detailed planning within the stated boundaries. Approval does not authorise uncontrolled changes, commitments beyond delegated limits, release without required evidence, or bypass of security, privacy, quality, financial and contractual controls.

# Appendix C - Project Plan Readiness Checklist

- ☐ Objectives are measurable and linked to the approved business need.

- ☐ Scope, exclusions, deliverables and acceptance criteria are complete and agreed.

- ☐ Requirements are prioritised, testable, traceable and owned.

- ☐ Work packages, estimates, dependencies and milestones are realistic.

- ☐ People, skills, tools, environments, procurement and funding are committed.

- ☐ Role separation meets Section 3.3 or approved compensating assurance is recorded.

- ☐ Quality, testing, assurance and evidence requirements are defined.

- ☐ Risk responses, issue management and escalation thresholds are active.

- ☐ Security, privacy, data, access, backup and continuity controls are defined where relevant.

- ☐ Stakeholder, communication, training and change-adoption plans are ready.

- ☐ Change, configuration, document and decision control methods are operating.

- ☐ Release, migration, support, rollback, handover and closure are planned.

- ☐ Benefits owner, review date, data source and protected review effort are approved.

- ☐ Sponsor and required reviewers have approved the baseline and any conditions.

## Planning Approval

| Role | Name | Decision / Conditions | Date |
| --- | --- | --- | --- |
| Sponsor |  |  |  |
| Project Manager |  |  |  |
| Technical / Quality Reviewer |  |  |  |
| Finance / Security / Operations as required |  |  |  |

# Appendix D - Project Status Report Template

| Field | Update |
| --- | --- |
| Project / Reporting period |  |
| Project class / Software class | Class A/B/C; where applicable Software Class 1/2/3/4: |
| Sponsor / Project manager |  |
| Overall status | Green / Amber / Red - evidence: |
| Tolerance position | Cost, schedule, scope, quality and risk forecast against approved limits: |
| Achievements this period |  |
| Planned next period |  |
| Milestones and forecast |  |
| Budget and resource forecast |  |
| Scope and approved changes |  |
| Quality, testing and acceptance |  |
| Top risks and issues |  |
| Decisions required | Decision, owner and required date: |
| Next routine or triggered Gate 5 | Date, trigger and accountable decision owner: |
| Year-One mandatory measures | Milestone reliability; cost forecast variance; first-pass acceptance; overdue critical actions; Gate 7 status: |
| Support / escalation needed |  |

## Status Certification

The project manager confirms that this report reflects the best current evidence and forecast available, including known adverse information. Material facts must not be omitted to preserve a favourable status.

# Appendix E - Risk and Issue Register Template

| ID | Risk / Issue | Likelihood | Impact | Owner | Response / Action | Due | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Risk Statement Guide

Use the form: Because of [cause], there is a possibility that [uncertain event], resulting in [effect on objectives]. For issues, state what has happened, the current impact, immediate containment, root-cause owner and resolution date.

## Escalation Record

| Date | Matter escalated | Decision owner | Decision / Conditions | Follow-up owner |
| --- | --- | --- | --- | --- |

# Appendix F - Change Request Template

| Field | Required information |
| --- | --- |
| Change ID / Date / Requester |  |
| Requested change and reason |  |
| Urgency and consequence of delay |  |
| Scope and requirements impact |  |
| Schedule and milestone impact |  |
| Cost, resources and procurement impact |  |
| Quality, security, privacy and operational impact |  |
| Risk, benefit and stakeholder impact |  |
| Options considered | Reject / defer / substitute / reduce other scope / approve / rebaseline. |
| Recommendation |  |
| Decision and conditions |  |
| Baseline and records updated by |  |
| Implementation verification |  |

# Appendix G - Project Closure Report Template

| Closure area | Evidence / outcome |
| --- | --- |
| Objectives and deliverables | Completed, partially completed or terminated; reasons and evidence. |
| Acceptance | Accepting authority, date, conditions and final version. |
| Schedule performance | Original baseline, approved changes, actual completion and explanation. |
| Financial performance | Approved budget, actual/committed cost, variance and reconciliation. |
| Quality and defects | Tests, accepted limitations, residual defects and owners. |
| Risks and issues | Closed, transferred or accepted items and responsible owners. |
| Operations and support | Handover, training, documentation, access, support and rollback readiness. |
| Contracts and assets | Supplier closure, licences, accounts, equipment and data disposition. |
| Lessons learned | Practices to retain, change or stop. |
| Benefits follow-up | Measures, baseline, targets, owners and review dates. |
| Register status after Gate 6 | Operational - Benefits Pending until Gate 7; record due date and evidence owner. |
| Retention and disposal | Record categories, custodians, disposal dates and any legal hold under Appendix J. |
| Closure decision | Approved / approved with actions / held; decision owner and date. |

# Appendix H - Responsibility and Decision Matrix

Each row has one accountable authority. Responsible roles perform or coordinate the work; consulted roles provide required challenge or evidence. The authority bands in Section 3.2 and the Class A rules below determine which row applies.

| Activity / condition | Accountable (one A) | Responsible | Consulted / evidence |
| --- | --- | --- | --- |
| Prioritise project and confirm class | Project Authority | Idea owner / Project Manager | Sponsor, Finance, Technical/Quality/Security as relevant |
| Approve Class A charter | Project Authority | Sponsor and Project Manager | Finance and independent control reviewer |
| Approve Class B/C charter | Project Sponsor | Project Manager | Project Authority for exceptions; relevant reviewers |
| Prepare integrated plan | Project Manager | Technical/Product leads and team | Sponsor, Finance, Assurance, Service Owner |
| Approve Class A baseline | Project Authority | Sponsor and Project Manager | Independent assurance and relevant control owners |
| Approve Class B/C baseline | Project Sponsor | Project Manager | Finance, Technical/Quality/Security/Service as relevant |
| Deliver work packages | Project Manager | Technical/Product lead and team | Sponsor and Assurance |
| Monitor and report | Project Manager | Workstream owners | Sponsor, Finance and Assurance |
| Approve material change within Sponsor limit | Project Sponsor | Project Manager | Finance and affected control owners |
| Approve material change beyond Sponsor limit or any Class A material rebaseline | Project Authority | Sponsor and Project Manager | Finance and independent control reviewer |
| Approve release / final acceptance | Named Acceptance Authority | Project Manager and Technical/Product leads | Sponsor, Service Owner and independent reviewers required by class |
| Approve closure | Project Sponsor | Project Manager and Service Owner | Finance, Assurance and Acceptance Authority |
| Complete Gate 7 benefits decision | Project Sponsor | Service / Operations Owner | Framework Owner, Finance and affected users |

# Appendix I - Project and Software Framework Reconciliation

Governing rule: Software projects must satisfy both this framework and the current approved edition of the KenAddme IT Links Software Development and Engineering Framework. Evidence is created once and referenced by both. The higher classification, stronger control and more senior approver govern whenever the mappings differ.

## I.1 Classification Mapping

| Project class | Normal software class mapping | Mandatory interpretation |
| --- | --- | --- |
| Class C - Small / Low Risk | Software Class 1 or Class 2 | Class 1 is permitted only for time-bound, non-production experimentation with no real personal, client-confidential or payment data. Any operational or production use is at least Class 2. |
| Class B - Standard / Medium Risk | Software Class 2 or Class 3 | Use Class 3 where personal/sensitive data, public exposure, finance/identity, material reputation, contractual service levels or significant recovery impact exists. |
| Class A - Strategic / High Risk | Software Class 3 or Class 4 | Use Class 4 for safety-significant, critical-infrastructure, large-scale restricted-data or mission-critical services. Executive governance and explicit residual-risk acceptance apply. |

## I.2 Gate Alignment and Evidence Reuse

| Project gate | Software checkpoint | Consolidation rule |
| --- | --- | --- |
| Gate 1 - Intake | G0 - Intake | Use one intake record, sponsor, feasibility screen and initial classification decision. |
| Gate 2 - Project Authorisation | G1 - Requirements Baseline | Combine when requirements and acceptance criteria are sufficiently mature. If G1 follows later, reuse the charter and add only the requirements evidence; do not repeat the business decision. |
| Gate 3 - Delivery Readiness | G2 - Design Readiness | Use one integrated readiness pack covering project baseline, architecture, security/privacy, test, deployment, assurance and operational plans. |
| Gate 4 - Release Readiness | G3 prerequisite and G4 - Release Readiness | G3 code-complete evidence is an engineering prerequisite. One G4/Gate 4 approval pack authorises release under the stricter approver set. |
| Gate 5 - Continuation / Exception | G3 or G5 evidence where relevant | Gate 5 is recurring or triggered project governance. Engineering or early-life evidence may support it; no duplicate gate is required solely because numbering differs. |
| Gate 6 - Closure | G5 - Operational Acceptance and G6 - Retirement/Closure | Use G5 evidence for handover. Use G6 when the project closes or a service is retired. One closure record may satisfy both where scope matches. |
| Gate 7 - Benefits | Post-implementation review evidence; no separate software gate | Use service measures and the software review as evidence for the single Gate 7 benefits decision. |

## I.3 Role Equivalence

| Project framework role | Software framework equivalent | Rule |
| --- | --- | --- |
| Project Sponsor | Sponsor | Same accountable business owner. |
| Project Manager | Delivery Lead / Project Manager | Coordinates the integrated project and software evidence. |
| Product / Business Owner | Product Owner | Owns user needs, backlog/requirements and functional acceptance. |
| Technical Lead | Solution Architect / Technical Lead | Owns architecture, engineering approach and technical risk. |
| Quality / Assurance Reviewer | QA / Test Engineer or independent assurance | Depth and independence follow the higher class. |
| Security / Privacy Reviewer | Security and Privacy Reviewer | Remains a distinct control role for higher-risk work. |
| Service / Operations Owner | Service Owner | Owns operational acceptance, support, continuity and benefits evidence. |
| Executive / Project Authority | Management / Release Authority (as defined in the software framework role table) | The stricter decision and quorum requirement applies. |

Both frameworks use 31 October 2026 as their effective date. The approved electronic copies are authoritative. If either framework is revised, the Framework Owner must review this reconciliation within ten business days and issue a controlled update where the mapping changes.

# Appendix J - Minimum Records Retention Schedule

The periods below begin at Gate 6 unless another event is stated. A longer legal, contractual, client, funder, tax, audit, dispute or incident requirement overrides the minimum. Retention must remain necessary, access-controlled and compatible with the Data Protection Act, 2012 (Act 843).

| Record category | Minimum retention | Owner / disposal rule |
| --- | --- | --- |
| Charter, business case, classifications, gate decisions, exceptions and closure report | 7 years after Gate 6 | Framework Owner / records custodian; preserve decision traceability. |
| Contracts, procurement, approvals, invoices, payment and financial reconciliation | 7 years after financial or contract closure | Finance/Administration; longer where tax, contract or public-procurement rules require. |
| Requirements, designs, deliverables, configuration, release, acceptance and operational handover | Life of the product/service plus 3 years, and never less than 7 years after Gate 6 | Technical and Service Owners; preserve the authoritative version and disposal evidence. |
| Risk, issue, change, quality, test, assurance, security and privacy records | 7 years after Gate 6 or final resolution, whichever is later | Project Manager and relevant control owner; incidents or investigations may impose a hold. |
| Benefits measures and Gate 7 evidence | 7 years after Gate 7 | Sponsor and Service / Operations Owner. |
| Unsuccessful bids, proposals and tender working files | 3 years after award/decline, unless dispute or client rule requires longer | Commercial/Finance owner; remove unnecessary personal data earlier. |
| Temporary working copies containing personal data | Only while necessary for the approved purpose; review at Gate 6 and at least annually | Data owner; delete or anonymise promptly when no longer needed and record the action. |
| Training, competence and framework-attendance records | 5 years after the activity | Framework Owner / Administration. |

Secure disposal: Disposal must be authorised, irreversible and recorded. Paper must be securely destroyed; digital copies, exports, backups and third-party holdings must be deleted or rendered inaccessible according to approved technical and contractual procedures.

# Institutional Adoption

This framework is approved as the minimum project-management standard for KenAddme IT Links. It applies during transition as stated in Section 20 and becomes fully mandatory on 31 October 2026. The approved electronic copy is authoritative; printed or exported copies are uncontrolled unless the version and approval status are verified before use.

Ownership and authority: Freston Kenny Adedeme owns and maintains this framework and authorises its institutional use by KenAddme IT Links. Changes to ownership, status, effective date, authority thresholds or mandatory controls require a controlled revision and recorded approval. Versioning convention: both institutional frameworks increment the second digit for a controlled minor revision and the first digit for a structural revision; a pre-approval edition is recorded as a draft of the version it becomes, and the approval date recorded in document control governs where a revision-history entry differs.

| Approval role | Name | Decision / record | Date |
| --- | --- | --- | --- |
| Document Owner / Approving Authority | Freston Kenny Adedeme | Approved electronically for institutional use | 2 September 2026 |
| Framework Custodian | Freston Kenny Adedeme | Ownership, annual review and controlled maintenance accepted | 2 September 2026 |
| Review Basis | Independent editorial and governance review | All eleven findings accepted and closed | 1-2 September 2026 |
| Institutional Use | KenAddme IT Links | Mandatory from common effective date | 31 October 2026 |

END OF FRAMEWORK